## Project Plan
Report | Task | Date
OR | Oregon Rep Licensure renewal Deadline | 2024-12-31
All | Review and upate product and study lists for 2024 | 2025-01-10
All | Reach out to vendor and stakeholders to request Q4 data | 2025-01-10
NV | Nevada Rep Registration Deadline | 2025-01-15
MD-FL | Miami-Dade, FL Lobbyist Registration Deadline | 2025-01-15
NV | Collect list of NV, OR, CT and Miami-dade registered reps for 2024 | 2025-01-16 | Contact RLDatix Life Sciences (formerly Porzio Life Sciences) to discover how we can support your compliance reporting! Our suite of solutions and professional services is designed to help you anticipate evolving requirements, reduce stress, and ensure accuracy. Visit us at www.RLDatixLifeSciences.com or contact us at info@RLDatixLifeSciences.com
All | Review and update report rules/assumptions for Federal, NV, OR and VT reports. | 2025-01-17
All | Final collection day for all 2024 data (spend and samples) | 2025-02-01
All | Complete initial review and remediation of all Q4 data | 2025-02-07
All | Reach out to stakeholders on remaining data issues/questions | Friday, February 7, 2025
All | Complete final review and remediation of Q4 data | 2025-02-11
All | Begin final sweep of 2024 data to identify potential dups, orphan records, credits and other data anomolies that may accumulate during the course of the year. | 2025-02-11
Federal | Register with IDM and Open Payments, or Re-certify in Open Payments; Nominate RLDLS Submitter | 2025-02-14
Federal | Generate initdial draft of Federal Report and begin necessary data clean up | 2025-02-14
NV | Generate draft NV report and begin necessary data cleanup | 2025-02-18
NV | Generate and submit final NV report. | 2025-02-27
NV | Nevada Disclosure Submission Deadline | 2025-03-01
OR | Generate draft OR report and begin necessary data cleanup | 2025-03-03
Federal Samples | Generate draft Federal samples report and begin necessary data cleanup | 2025-03-03
Federal | Generate second draft Federal Report and begin necessary data clean up | 2025-03-03
VT | Generate draft VT report and begin necessary data cleanup; identify potential VT gift ban violations | 2025-03-10
Federal | Generate final Federal report and begin upload to Open Payments | 2025-03-10
Federal | Complete Federal report validation clean up in Open Payments | 2025-03-18
Federal | Complete Federal report attestation in Open Payments | Monday, March 24, 2025
OR | Generate and submit final OR report | 2025-03-25
VT | Genertae and submit final VT report; submit VT Compliance Officer form | Wednesday, March 26, 2025
Federal Samples | Generate and submit final Federal samples report | Thursday March 27, 2025
Federal | Federal Open Payments Deadline | 2025-03-31
OR | Oregon Rep Disclosure Deadline | 2025-04-01
VT | Vermont Spend and Sample Disclosure deadline and Compliance Officer form Deadline | 2025-04-01
MN | Review and update report rules/assumptions for MN report. | 2025-04-07
MN | Generate draft MN report and begin necessary data cleanup; identify potential MN gift ban violations | 2025-04-10
MN | Generate and submit final MN report | 2025-04-17
MN | Minnesota Report Due | 2025-05-01
All | Review and update report rules/assumptions for Miami-dade, DC, MA and CT reports. | 2025-05-05
MD-FL | Generate draft Miami-dade report and being necessary data cleanup | 2025-05-12
DC | Generate draft DC report and being necessary data cleanup | 2025-05-19
MD-FL | Generate and submit final Miami-dade report | 2025-05-22
CT PMF | Generate draft CT PMF report and being necessary data cleanup | 2025-05-26
CT APRN | Generate draft CT APRN report and being necessary data cleanup | 2025-05-26
MA | Generate draft MA report and being necessary data cleanup | 2025-06-02
DC | Generate and submit final DC report | 2025-06-09
CT PMF | Generate and submit final CT PMF report | 2025-06-12
CT PMF | Generate and submit final CT APRN report | 2025-06-12
MA | Generate and submit final MA report | 2025-06-16
CA | Generate CA audit report and begin necessary data evaluation | 2025-06-17
CA | Post CA public declaration on website | 2025-06-24
CT APRN | CT APRN Submission Deadline | 2025-06-30
CT PMF | Connecticut PMF submission and License Renewal Deadline | 2025-06-30
DC | DC Submission Deadline | 2025-07-01
MA | Massachusetts Submission Deadline | 2025-07-01
MD-FL | Miami-Dade, FL Lobbyist Disclosure Deadline | 2025-07-01